## WBS
E-Commerce WBS
#DIV/0! | Module name | Hours
1 | Core Foundation
1.1 | Repo setup for API + admin + storefront | 3
1.2 | workspace setup for API + admin + storefront | 3
1.3 | Environment management | 2
1.4 | config management | 2
1.5 | Global API response contract | 2
1.6 | Global API error contract | 3
1.7 | Base middleware stack (auth, validation, logging hooks) | 3
1.8 | Module registry skeleton | 2
1.9 | Seed scripts for baseline data | 2
1.10 | bootstrap scripts for baseline data | 2
2 | Auth And RBAC
2.1 | Admin login | 2
2.2 | Admin logout | 2
2.3 | Customer register | 2
2.4 | Customer login | 3
2.5 | Customer logout | 3
2.6 | Password reset flow | 2
2.7 | Access token lifecycle | 3
2.8 | refresh token lifecycle | 3
2.9 | Roles create | 3
2.10 | Roles edit | 3
2.11 | Roles delete | 3
2.12 | Permission mapping + API guard enforcement | 4
2.13 | Auth-related audit log events | 1
3 | Store Settings And Module Control
3.1 | Store profile create | 2
3.2 | Store profile update | 2
3.3 | Policy pages create | 2
3.4 | Policy pages edit | 2
3.5 | Policy pages publish | 2
3.6 | Module enable backend enforcement | 3
3.7 | Module disable backend enforcement | 3
3.8 | Module control screens in admin | 3
4 | Categories
4.1 | Category create | 2
4.2 | Category edit | 2
4.3 | Category delete (with parent validation) | 1
4.4 | Category delete (with child validation) | 1
4.5 | Category list | 1
4.6 | Category search | 1
4.7 | Category pagination | 1
4.8 | Storefront category tree endpoint + caching | 2
5 | Products And Variants
5.1 | Product create | 3
5.2 | Product edit | 3
5.3 | Product delete | 1
5.4 | Product archive | 1
5.5 | Product list (admin) | 3
5.6 | Product filter (admin) | 3
5.7 | Product search (admin) | 3
5.8 | Product publish status control | 1
5.9 | Product unpublish status control | 1
5.10 | Variant create | 2
5.11 | Variant edit | 2
5.12 | Variant delete | 1
5.13 | Product image upload | 4
5.14 | Product image order | 4
5.15 | Product image update | 4
5.16 | Product image remove | 4
5.17 | SEO and compliance fields integration | 3
5.18 | Slug validation and uniqueness rules | 2
5.19 | SKU validation and uniqueness rules | 2
5.20 | Storefront product list optimization | 3
5.21 | Storefront product detail optimization | 3
6 | Inventory
6.1 | Inventory stock model and migration | 3
6.2 | Stock adjustment create | 3
6.3 | Stock adjustment reverse handling | 2
6.4 | Stock adjustment correction handling | 2
6.5 | Inventory movement log automation | 3
6.6 | Reservation engine with order lifecycle | 6
6.7 | release engine with order lifecycle | 6
6.8 | Low-stock threshold and rule handling | 3
6.9 | Admin inventory list views | 3
6.10 | Admin inventory history views | 4
6.11 | Concurrency protection for stock writes | 2
7 | Cart
7.1 | Guest cart token lifecycle | 3
7.2 | Cart add item | 3
7.3 | Cart update quantity | 2
7.4 | Cart remove item | 2
7.5 | Cart totals recalculation pipeline | 4
7.6 | Guest cart merge with logged-in customer cart | 3
7.7 | Cart API recovery handling | 3
7.8 | Cart state recovery handling | 3
8 | Checkout And Order Creation
8.1 | Checkout validation pipeline | 3
8.2 | Saved address support in checkout | 3
8.3 | new address support in checkout | 3
8.4 | Delivery zone resolve during checkout | 4
8.5 | Delivery rate resolve during checkout | 4
8.6 | Atomic order creation transaction | 6
8.7 | Idempotency handling for checkout submit | 3
8.8 | Price snapshot storage on order items | 3
8.9 | Failure rollback and stock compensation | 4
8.10 | Order confirmation response | 4
8.11 | Order confirmation events | 4
9 | Orders And Fulfillment
9.1 | Admin order list | 4
9.2 | Admin order filter | 4
9.3 | Admin order detail timeline | 3
9.4 | Order status transition engine and rules | 7
9.5 | Order status history tracking | 3
9.6 | Admin order notes | 2
9.7 | Cancel flow with stock reconciliation | 3
9.8 | Basic return request flow request | 4
9.9 | Basic return request flow approve | 4
9.10 | Basic return request flow reject | 4
9.11 | Basic return request flow received | 4
9.12 | Invoice and packing slip generation | 4
10 | Payments (MVP)
10.1 | Payment entity and payment state model | 4
10.2 | COD payment workflow | 3
10.3 | Admin manual payment update controls | 2
10.4 | Gateway adapter interface and mock adapters | 5
10.5 | Order-payment state sync rules | 3
11 | Customers
11.1 | Customer list (admin) | 2
11.2 | Customer filter (admin) | 2
11.3 | Customer search (admin) | 2
11.4 | Customer profile detail | 1
11.5 | Customer address create | 3
11.6 | Customer address edit | 3
11.7 | Customer address delete | 3
11.8 | Customer order history | 2
11.9 | Internal notes for support workflow | 2
11.10 | Internal tags for support workflow | 2
12 | Content And Policy Pages
12.1 | Policy page create | 1
12.2 | Policy page edit | 1
12.3 | Policy page delete | 1
12.4 | Policy page publish | 1
12.5 | content page create | 1
12.6 | content page edit | 1
12.7 | content page delete | 1
12.8 | content page publish | 1
12.9 | Homepage banner block management | 2
12.10 | Footer content management | 1
12.11 | contact content management | 1
13 | Promotions/Coupons
13.1 | Coupon create | 4
13.2 | Coupon edit | 4
13.3 | Coupon delete | 4
13.4 | Coupon validation engine in checkout | 4
13.5 | Coupon usage limits and expiry handling | 3
13.6 | Offer scheduling baseline | 2
13.7 | campaign scheduling baseline | 3
13.8 | Coupon usage reporting (basic) | 2
14 | Dashboard And Reports
14.1 | Dashboard KPI aggregation | 5
14.2 | Sales report | 4
14.3 | Orders report | 4
14.4 | Inventory report | 3
14.5 | Customer report | 4
14.6 | Export jobs CSV | 4
14.7 | Export jobs XLSX | 4
15 | Security, Audit, And Logging Baseline
15.1 | Audit log event model and storage | 3
15.2 | Rate limiting auth endpoints | 3
15.3 | Rate limiting checkout endpoints | 3
15.4 | Rate limiting public endpoints | 3
15.5 | Input validation hardening | 3
15.6 | Permission boundary hardening | 3
15.7 | Structured logging and error-trace hooks | 4
16 | CI/CD And Deployment Automation
16.1 | Dockerization and environment templates | 4
16.2 | CI pipeline lint | 3
16.3 | CI pipeline test | 3
16.4 | CI pipeline build | 3
16.5 | CD flow for staging and production | 4
16.6 | Backup automation scripts | 3
16.7 | restore automation scripts | 4
16.8 | Release and rollback automation checklist | 3
442
17 | Shipping And Courier (MVP)
17.1 | Delivery zone create | 3
17.2 | Delivery zone edit | 3
17.3 | Delivery zone delete | 3
17.4 | Delivery rate rule create | 3
17.5 | Delivery rate rule edit | 3
17.6 | Delivery rate rule delete | 3
17.7 | Shipment create from order | 2
17.8 | Shipment assign from order | 2
17.9 | Tracking ID update | 1
17.10 | Tracking URL update | 1
17.11 | Shipment state transitions and mapping | 3
17.12 | Courier webhook normalization | 2
17.13 | Courier webhook idempotency | 2
17.14 | Courier adapter interface stubs | 2
18 | Multi-Vendor Activation And Gating
18.1 | Commerce mode switch and config controls | 2
18.2 | Multi-vendor module route gating | 3
18.3 | Multi-vendor module API gating | 3
18.4 | Multi-vendor module UI gating | 3
18.5 | Backward compatibility for single-vendor clients | 2
19 | Vendor Onboarding And Access
19.1 | Vendor invite | 3
19.2 | Vendor self-registration | 2
19.3 | Vendor profile create | 2
19.4 | Vendor profile edit | 2
19.5 | Vendor approve | 2
19.6 | Vendor reject | 2
19.7 | Vendor suspend | 2
19.8 | Vendor reactivate | 2
19.9 | Vendor login reset | 2
19.10 | Vendor session reset | 2
19.11 | Vendor password reset | 2
19.12 | Vendor role baseline | 3
19.13 | Vendor permission baseline | 3
20 | Vendor Catalog Governance
20.1 | Vendor product create | 3
20.2 | Vendor product edit | 2
20.3 | Vendor product delete | 2
20.4 | Vendor product archive | 2
20.5 | Admin product approval workflow | 4
20.6 | Admin product rejection workflow | 4
20.7 | Vendor media validation | 3
20.8 | Vendor compliance validation | 3
20.9 | Vendor catalog list | 2
20.10 | Vendor catalog search | 2
20.11 | Vendor catalog filter | 3
20.12 | Vendor catalog notifications | 2
20.13 | Vendor catalog audit trails | 2
21 | Vendor Inventory Boundaries
21.1 | Vendor-scoped stock visibility | 4
21.2 | Vendor stock adjust with strict ownership checks | 5
21.3 | Cross-vendor stock isolation policy enforcement | 5
21.4 | Vendor low-stock alert jobs | 3
22 | Vendor Order Split And Processing
22.1 | Split order items by vendor during order creation | 8
22.2 | Vendor order list | 4
22.3 | Vendor order filter | 5
22.4 | Vendor order detail and item actions | 5
22.5 | Vendor-allowed status transitions | 5
22.6 | Vendor sub-shipment handling | 5
22.7 | Vendor cancel request workflow | 5
22.8 | Vendor refund request workflow | 5
22.9 | Vendor order history and audit tracking | 4
23 | Commission And Payout
23.1 | Commission rule create | 5
23.2 | Commission rule edit | 5
23.3 | Commission calculation engine | 7
23.4 | Vendor earnings ledger | 4
23.5 | Payout request workflow | 5
23.6 | Manual payout settlement + references | 4
23.7 | Commission reports | 5
23.8 | payout reports | 4
24 | Vendor Portal UI
24.1 | Vendor dashboard KPIs | 5
24.2 | Vendor product screens | 6
24.3 | Vendor inventory screens | 4
24.4 | Vendor order screens | 5
24.5 | Vendor earnings screens | 4
24.6 | Vendor payout screens | 4
24.7 | Vendor profile screens | 4
24.8 | Vendor settings screens | 4
25 | Marketplace Security Hardening
25.1 | Vendor scope middleware deep hardening | 6
25.2 | Object-level authorization tests and fixes | 5
25.3 | Anti-fraud controls for sensitive vendor actions | 4
25.4 | Expanded audit hooks for vendor operations | 5
25.5 | Marketplace Reports And Admin Controls | 18
25.6 | Marketplace sales report | 5
25.7 | Vendor performance report | 5
25.8 | Commission liability report | 4
25.9 | Admin marketplace filters and controls | 4
25.10 | Rollout, Migration, And Recovery Tooling | 15
25.11 | Enablement migration scripts for existing clients | 5
25.12 | Feature-flag rollout scripts and controls | 4
25.13 | Multi-vendor module rollback scripts | 3
25.14 | Post-launch monitoring setup updates | 3