## Phase 2
18 | Multi-Vendor Activation And Gating
18.1 | Commerce mode switch and config controls | 2
18.2 | Multi-vendor module route gating | 3
18.3 | Multi-vendor module API gating | 3
18.4 | Multi-vendor module UI gating | 3
18.5 | Backward compatibility for single-vendor clients | 2
19 | Vendor Onboarding And Access
19.1 | Vendor invite | 3
19.2 | Vendor self-registration | 2
19.3 | Vendor profile create | 2
19.4 | Vendor profile edit | 2
19.5 | Vendor approve | 2
19.6 | Vendor reject | 2
19.7 | Vendor suspend | 2
19.8 | Vendor reactivate | 2
19.9 | Vendor login reset | 2
19.10 | Vendor session reset | 2
19.11 | Vendor password reset | 2
19.12 | Vendor role baseline | 3
19.13 | Vendor permission baseline | 3
20 | Vendor Catalog Governance
20.1 | Vendor product create | 3
20.2 | Vendor product edit | 2
20.3 | Vendor product delete | 2
20.4 | Vendor product archive | 2
20.5 | Admin product approval workflow | 4
20.6 | Admin product rejection workflow | 4
20.7 | Vendor media validation | 3
20.8 | Vendor compliance validation | 3
20.9 | Vendor catalog list | 2
20.10 | Vendor catalog search | 2
20.11 | Vendor catalog filter | 3
20.12 | Vendor catalog notifications | 2
20.13 | Vendor catalog audit trails | 2
21 | Vendor Inventory Boundaries
21.1 | Vendor-scoped stock visibility | 4
21.2 | Vendor stock adjust with strict ownership checks | 5
21.3 | Cross-vendor stock isolation policy enforcement | 5
21.4 | Vendor low-stock alert jobs | 3
22 | Vendor Order Split And Processing
22.1 | Split order items by vendor during order creation | 8
22.2 | Vendor order list | 4
22.3 | Vendor order filter | 5
22.4 | Vendor order detail and item actions | 5
22.5 | Vendor-allowed status transitions | 5
22.6 | Vendor sub-shipment handling | 5
22.7 | Vendor cancel request workflow | 5
22.8 | Vendor refund request workflow | 5
22.9 | Vendor order history and audit tracking | 4
23 | Commission And Payout
23.1 | Commission rule create | 5
23.2 | Commission rule edit | 5
23.3 | Commission calculation engine | 7
23.4 | Vendor earnings ledger | 4
23.5 | Payout request workflow | 5
23.6 | Manual payout settlement + references | 4
23.7 | Commission reports | 5
23.8 | payout reports | 4
24 | Vendor Portal UI
24.1 | Vendor dashboard KPIs | 5
24.2 | Vendor product screens | 6
24.3 | Vendor inventory screens | 4
24.4 | Vendor order screens | 5
24.5 | Vendor earnings screens | 4
24.6 | Vendor payout screens | 4
24.7 | Vendor profile screens | 4
24.8 | Vendor settings screens | 4
25 | Marketplace Security Hardening
25.1 | Vendor scope middleware deep hardening | 6
25.2 | Object-level authorization tests and fixes | 5
25.3 | Anti-fraud controls for sensitive vendor actions | 4
25.4 | Expanded audit hooks for vendor operations | 5
26 | Marketplace Reports And Admin Controls | 18
26.1 | Marketplace sales report | 5
26.2 | Vendor performance report | 5
26.3 | Commission liability report | 4
26.4 | Admin marketplace filters and controls | 4
27 | Rollout, Migration, And Recovery Tooling | 15
27.1 | Enablement migration scripts for existing clients | 5
27.2 | Feature-flag rollout scripts and controls | 4
27.3 | Multi-vendor module rollback scripts | 3
27.4 | Post-launch monitoring setup updates | 3
11 | Shipping And Courier (MVP)
11.1 | Delivery zone create | 3
11.2 | Delivery zone edit | 3
11.3 | Delivery zone delete | 3
11.4 | Delivery rate rule create | 3
11.5 | Delivery rate rule edit | 3
11.6 | Delivery rate rule delete | 3
11.7 | Shipment create from order | 2
11.8 | Shipment assign from order | 2
11.9 | Tracking ID update | 1
11.10 | Tracking URL update | 1
11.11 | Shipment state transitions and mapping | 3
11.12 | Courier webhook normalization | 2
11.13 | Courier webhook idempotency | 2
11.14 | Courier adapter interface stubs | 2